| Period of time | EU-MED AgPol WPs | MEDFROL WPs | Cooperation | EU-MED AGPOL specific contributions | MEDFROL specific contributions |
| --- | --- | --- | --- | --- | --- |
| March 2004 – March 2007 | Full project duration March 2004 – Feb. 2007 | Full project duration April 2004 – March 2007 | To provide free access to each project’s database and web sites: Coordinators have to allocate access codes (for the web sites) to other project’s partners http://medfrol.maich.gr http://eumed-agpol.iamm.fr To design a web page on the web site of CIHEAM presenting the cooperation between both projects(www.ciheam.org) To institute regular communications between the projects’ coordinators and hold meetings of the joint advisory group as foreseen previously. The project coordinators will facilitate communication between researchers in common areas. | Organisation of meetings and workshops as has been agreed by the EU (i.e. Technical Annex – EU-MED AGPOL) | Organisation of meetings and workshops as has been agreed by the EU (i.e. Technical Annex – MEDFROL) |
| March 2004 – July 2005 | WP 1 March 2004 – May 2005 WP 2 March 2004 – July 2005 | WP A April 2004 – March 2005 WP B Nov. 2004 – April 2005 | To implement strong collaboration among partners working in both projects on the same countries in order: To exchange ‘raw data’ and to formulate one common enlarged database To assure the complementarity of the reports and to avoid overlapping | To provide: Data already assembled on the Mediterranean countries Reports on the Agricultural Sector with special emphasis on fruits, vegetables, olive oil and processed foods for Morocco, Turkey, Tunisia, Egypt and Israel (D2, D3, D4, D5, D6) Organisation of a meeting (in Montpellier or Brussels) for the advisory committee in September 2004 which will relay the reports of the WP1/WPA Reports on the European Production and Markets for fruits and vegetables (France, Portugal, and Italy) (D8, D9) Reports on the European Olive Oil Production and Markets (Spain, Italy, France and Portugal) (D10) | To provide: Agricultural situation reports for Cyprus, Israel, Lebanon, Malta, Turkey, Syria, Jordan, Morocco, Libya, Algeria, Tunisia, Gaza Strip and Egypt (D7, D8, D9, D10) Draft reports on national agricultural policies for Cyprus, Israel, Lebanon, Malta, Turkey, Syria, Jordan, Morocco, Libya, Algeria, Tunisia, Gaza Strip and Egypt (D2, D3, D4, D5) Report on fruits and vegetables for Spain (part of D11) Report on fruits and vegetables and on the olive oil for Greece (D12) Description of the supply chain for fruits and vegetables in the EU (Germany and the Netherlands) (D17) |
| March 2003 - May 2005 | WP3 March 2004 – May 2005 |  | To use a common data base on existing protection systems | Description and quantification of the EU protection systems for fruits, vegetables, and olive oil (part of D13 and D14) |  |
| May 2005 – August 2005 | WP 4 June 2005 – August 2005 | WP E May 2005 – Sept. 2006 | To develop the liberalisation scenarios, with the consultation of the EC officers | Participate in the development of the policy scenarios | Organisation of a teleconference or meeting in Brussels in May 2005 |
| Dec. 2004 – Nov. 2006 | WP 5, 6, and 7 June 2005 – August 2006 | WP C, D, E, and F Dec. 2004 – Nov. 2006 | To exchange preliminary results so that the different approaches used by the two teams can be enriched by the insight gained from the other approaches | Organisation of a technical meeting for the advisory committee in March 2006 to review preliminary results from both teams (joint meeting) | Organisation of a workshop for the advisory committee in October 2006 |
| June 2004 – March 2007 | WP 9 June 2004 – Feb. 2007 | WP G and H August 2004 – March 2007 | To exchange results and reports Plan and conduct a joint conference near the end of the projects To publish common work |  | Organisation of the final seminar in March 2007 in a place to specify (joint meeting) |

Note: Cooperation will also be implemented with other EU projects as well dealing with relevant topics.

| EU-MED AgPol WPs |
| --- |
| WP | WP title |
| 1 | Characterize the agricultural and agro-industry sectors in Mediterranean countries |
| 2 | Characterize the agricultural sectors in major European regions for production of fruits, vegetables, and olive oil |
| 3 | Describe and quantify the EU protection systems for fruits, vegetables, and olive oil |
| 4 | Develop specific liberalization scenarios |
| 5 | Estimate the production and export potential for each Mediterranean country |
| 6 | Quantify possible changes in European and Mediterranean production, imports, and exports of important commodities |
| 7 | Interaction with world markets and international negotiations |
| 8 | Estimate the changes in European production, incomes, ag budgets, social changes, and other impacts |
| 9 | Diffuse results |

| MEDFROL WPs |
| --- |
| WP | WP title |
| A | Presentation of the general economic environment and agriculture with emphasis on the fruit and vegetables and olive oil sectors in the Mediterranean regions |
| B | Fruit and vegetables and olive oil supply chain analysis in the EU |
| C | Productivity/efficiency and import demand models specification and selection of case studies |
| D | Productivity and import demand analysis |
| E | Trade and policy model |
| F | Input-Output model |
| G | Dissemination of results |
| H | Final Report |